Introduction to Software Engineering

Weekly Status Report

The student team is required to complete the Weekly Status Report documentation for the assigned course project, following the attached template.

Software Engineering Department

Faculty of Information and Technology

University of Science

Table of Contents

Right-click here and choose “Update Field” to build the table of contents.

Weekly Status Report

# Objectives

This document focus on the following topics:

- Reporting weekly progress against the project plan

- Recording issues and risks

- Recording the weekly status meeting

# Submission

- One report per week, from week 2 to week 10 (9 reports). The team lead (or backup) is responsible.

- The team chooses its own weekly deadline (e.g., the day after the status meeting) and states it in PA1.

- Commit the report to the repository: /docs/management/weekly/W<week>-status.docx (or .md), e.g., W03-status.docx. Do not overwrite or rewrite earlier reports; the commit history is the evidence of timeliness.

- Reports are not submitted on Moodle. They are graded at the end of the course as part of the Teamwork & tool usage component (working process).

# Report Information

| Item | Value |
| --- | --- |
| Team | T05 – Nexora ¦ CourtMate |
| Week | W04 – 19/10/2026 to 25/10/2026 (Asia/Ho_Chi_Minh) |
| Date of meeting | Not verified. Work updates recorded asynchronously through GitHub Issues/PRs. |
| Current phase / PA | PA1 closure and archiving; PA2 – Software Requirements Specification |
| Prepared by | Nguyễn Đức Hưng – Team Lead ¦ prepared 26/10/2026 |
| Overall status | AMBER (at risk): PA1 archived; PA2 component documents merged, but integrated SRS/BR evidence and meeting record require confirmation. |

## Task Status

Task owners and PA2 deadlines follow GitHub Issues #60–#63. Evidence is the linked PR/commit history. An issue marked closed is not treated as proof that its deliverable is on main.

| WBS / task | Owner | Planned finish | Status | % done | Notes |
| --- | --- | --- | --- | --- | --- |
| PA1 closeout | Hưng/Trung | 20/10 | Done | 100% | PR #51, #56–59 merged |
| PA2 #60 – FR/AC | Hưng | 30/10 | Done | 100% | PR #68 merged 24/10 |
| PA2 #61 – FR/AC | Trung | 30/10 | Done | 100% | PR #70 merged 25/10 |
| PA2 #62 – NFR | Hiếu | 30/10 | Done | 100% | PR #64 merged 23/10 |
| PA2 #63 – BR | Quang | 30/10 | Done | 100% | PR #71 merged 26/10 |

## Plan for Next Week

| WBS / task | Owner | Planned finish |
| --- | --- | --- |
| PA2 SRS: policy and consistency review | Hưng/Quang + team | 30–31/10 |
| UC, mockups, RTM, review and AI log | Team (assign on review) | 31/10–01/11 |
| Figma / PA2 UI consistency | Hiếu/Hưng (proposed) | 31/10 |
| Bootstrap review and PA3 planning | Hưng + reviewers | 01/11 |

## Issues and Risks

| ID | Description | Impact | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| R01 | 8 Must features; short PA5 window | Schedule risk | Prioritize Must; revise WBS | Hưng/team | PA3 |
| R02 | Booking/room policies pending review | SRS/UI mismatch | Review FR/BR/AC and UI | Hưng/Quang | 31/10 |
| I01 | BR artifact and meeting proof N/V | Weak evidence | Collect BR file and minutes | Quang/Hưng | 30/10 |

## Meeting Minutes

During W04, the team held two meetings to coordinate PA2 development and review the CourtMate SRS.

Meeting 1 – Task Assignment: The team assigned PA2 responsibilities across Sections 1–5, designated reviewers, and agreed on deliverables and deadlines. GitHub Issues #60–#63 were created to track individual assignments.

Meeting 2 – SRS Review and Alignment: The team reviewed the consolidated Functional Requirements, Non-Functional Requirements, Business Rules, and Acceptance Criteria. Key discussions covered booking availability, cancellation policies, Court Owner permissions, Open Play Rooms, and requirement consistency. The team agreed to maintain a unified SRS for subsequent use case modeling, UI design, and testing.

During the week, PA2 PRs #64, #68, and #70 were merged. Final document integration and cross-section validation remained follow-up activities.

| Member | Present | Done since last meeting | Next | Blockers |
| --- | --- | --- | --- | --- |
| Nguyễn Đức Hưng | Yes | PA1 closeout; PA2 Sections 1–4, FR/AC; PR #68; SRS coordination | Consolidate SRS; verify FR–BR–AC alignment | None reported |
| Dương Trung Hiếu | Yes | NFR-01–05; PR #64; PA1 AI log | Review UI against SRS; support NFR verification | None reported |
| Lê Thành Trung | Yes | PA2 F03/F05/F07/F08/F09 and AC; PR #70 | Review use cases, acceptance criteria and prototype consistency | None reported |
| Bùi Phạm Quang | Yes | PA2 Business Rules; Issue #63; SRS policy review | Finalize Business Rules; cross-check FR, NFR and AC consistency; support SRS review | None reported |

## Metrics

| Metric | This week | Total |
| --- | --- | --- |
| Tasks completed | 5 verified items; #63 needs artifact | Cumulative WBS not verified |
| Commits | 16 main + 1 bootstrap branch | 38 on main |
| Pull requests merged / reviewed | 8 merged; reviews N/V | 17 merged total |
| Open defects (PA5) | N/A (before PA5) | N/A |

Evidence: PRs #51, #56–#59, #64, #68, #70; Issues #60–#63. Repo: https://github.com/hungstupid/CourtMate

PA2 PRs: https://github.com/hungstupid/CourtMate/pull/64 ; /pull/68 ; /pull/70 (under same repository).

Bootstrap evidence: commit b7a393b on chore/project-bootstrap (25/10); not merged as of W04.

Reporting boundary: 19–25/10/2026. Changes dated 26/10 or later are excluded.